## Title
VMware Solution
VMware and Customer Confidential
VMware Pro Cloud Service for Private Cloud Infrastructure
Component: VMware Cloud Foundation Automation
Engagement Work Breakdown Structure
for
<Customer>
Prepared by
<Consultant>
Professional Services | VMware by Broadcom
<consultant>@broadcom.com

## VCFA WBS
VMware Cloud Foundation Automation - Work Breakdown Structure
Backlog Item | Task | Architect | Senior Consultant | Project Manager
|  | Total hours | Total hours | Total hours
Project Management Oversight - 30% | Project Management Oversight |  |  | 12
VMware Cloud Foundation Automation Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Discuss Environmental requirements for VCF Automation design workshop | 2
VMware Cloud Foundation Automation Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Discuss and Determine roles and service accounts will be used and who will be responsible for each role | 1
VMware Cloud Foundation Automation Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Develop the implementation plan | 2
VMware Cloud Foundation Automation Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Finalize the service checklist documentation | 1
VMware Cloud Foundation Automation Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Design Workshop - Review | 2
VMware Cloud Foundation Automation Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Finalize the architecture design documentation | 4
VMware Cloud Foundation Automation Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Finalize the configuration workbook documentation | 2
VMware Cloud Foundation Automation Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Finalize the requirements workbook documentation | 2
VMware Cloud Foundation Automation Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Validation of the prerequisites for the VCF Automation Deployment /Configurations |  | 1
VMware Cloud Foundation Automation Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Verify customer VM network, Active Directory, vCenter infrastructure and virtual machine templates are ready and available |  | 1
VMware Cloud Foundation Automation Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Verify the Load Balancer VIP CNAMES for the Appliances FQDNs are configured and registered properly in DNS |  | 0.5
VMware Cloud Foundation Automation Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Import the certificates for the VCF Automation appliances |  | 1
VMware Cloud Foundation Automation Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Cloud Assembly - Configure Cloud Accounts |  | 0.5
VMware Cloud Foundation Automation Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Cloud Assembly - Configure Projects, Cloud Zones, Flavor Mappings, Image Mappings, Network Profiles, and Storage Profiles |  | 2
VMware Cloud Foundation Automation Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Cloud Assembly - Download Blueprints from Marketplace |  | 1
VMware Cloud Foundation Automation Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Finalize the Configuration Workbook with the VCF Automation Configuration |  | 2
VMware Cloud Foundation Automation Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Operational Enablement - Service Catalog Management Workshop |  | 2
VMware Cloud Foundation Automation Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Operational Enablement - Troubleshooting, Event and Log Management Workshop |  | 2
VMware Cloud Foundation Automation Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Operational Enablement - Enable customer on Startup/Shutdown procedures |  | 2
VMware Cloud Foundation Automation Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Operational Enablement - Single Machine Blueprint Creation Workshop |  | 2
VMware Cloud Foundation Automation Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Operational Enablement - Custom Forms, Actions, and Subscriptions Workshop |  | 2