## Analysis (hidden)
5.2 Backlog | 5.2 WBS Name | 9.0 Backlog | 9.0 WBS Name | Role | 5.2 WBS LOE | 9.0 WBS LOE | Delta | 5.2 PSST LOE | 9.0 PSST LOE
Design and Deploy VMware Cloud Foundation 5.x (see task details tab) | VCF | Virtualized Infrastructure 9.x | VCF | Architect | 104 | 154 | 50
Design and Deploy VMware Cloud Foundation 5.x (see task details tab) | VCF | Virtualized Infrastructure 9.x | VCF | Sr. Consultant | 152 | 226 | 74
Design and Deploy VMware Cloud Foundation 5.x | VCF | Virtualized Infrastructure 9.x | VCF | PM | 70 | 70 | 0
Design and Deploy NSX with VMware Cloud Foundation 5.x |  | Virtualized Infrastructure 9.x |  | Architect |  |  | 0
Design and Deploy NSX with VMware Cloud Foundation 5.x |  | Virtualized Infrastructure 9.x |  | Sr. Consultant |  |  | 0
Design and Deploy NSX with VMware Cloud Foundation 5.x |  | Virtualized Infrastructure 9.x |  | PM |  |  | 0
Deploy Security Hardening for VMware Cloud Foundation | VCF_Security | Security Governance, and Compliance 9.x | VCF_Security | Architect | 140 | 140 | 0
Deploy Security Hardening for VMware Cloud Foundation | VCF_Security | Security Governance, and Compliance 9.x | VCF_Security | PM | 35 | 35 | 0
Design and Implement Aria Suite Lifecycle and Access Management With VMware Cloud Foundation 5.x | ASLC | Virtualized Infrastructure 9.x |  | Architect | 4 |  | -4
Design and Implement Aria Suite Lifecycle and Access Management With VMware Cloud Foundation 5.x | ASLC | Virtualized Infrastructure 9.x |  | Sr. Consultant | 8 |  | -8
Design and Implement Aria Suite Lifecycle and Access Management With VMware Cloud Foundation 5.x | ASLC | Virtualized Infrastructure 9.x |  | PM | 3.6 |  | -3.6
Design and Deploy VMware Cloud Foundation® Operations for networks for VMware Cloud Foundation® 5.x | AOPS | Automated Operations 9.x | VCFO | Architect | 16 | 16 | 0
Design and Deploy VMware Cloud Foundation® Operations for networks for VMware Cloud Foundation® 5.x | AOPS | Automated Operations 9.x | VCFO | Sr. Consultant | 16 | 24 | 8
Design and Deploy VMware Cloud Foundation® Operations for networks for VMware Cloud Foundation® 5.x | AOPS | Automated Operations 9.x | VCFO | PM | 12 | 12 | 0
Design and Deploy VCF Operations for Logs for VMware Cloud Foundation 5.x | AOPS4L | Automated Operations 9.x | VCFOL | Architect | 10 | 8 | -2
Design and Deploy VCF Operations for Logs for VMware Cloud Foundation 5.x | AOPS4L | Automated Operations 9.x | VCFOL | Sr. Consultant | 12 | 12 | 0
Design and Deploy VCF Operations for Logs for VMware Cloud Foundation 5.x | AOPS4L | Automated Operations 9.x | VCFOL | PM | 6 | 6 | 0
Design and Deploy VMware Cloud Foundation® Operations for networks for VMware Cloud Foundation® 5.x | AOPS4N | Virtualized Infrastructure 9.x | VCFON | Architect | 5 | 9 | 4
Design and Deploy VMware Cloud Foundation® Operations for networks for VMware Cloud Foundation® 5.x | AOPS4N | Virtualized Infrastructure 9.x | VCFON | Sr. Consultant | 16 | 15 | -1
Design and Deploy VMware Cloud Foundation® Operations for networks for VMware Cloud Foundation® 5.x | AOPS4N | Virtualized Infrastructure 9.x | VCFON | PM | 7.2 | 7.2 | 0
Design and Deploy VCF Automation for VMware Cloud Foundation 5.x | AA | Virtualized Infrastructure 9.x | VCFA | Architect | 16 |  | -16
Design and Deploy VCF Automation for VMware Cloud Foundation 5.x | AA | Virtualized Infrastructure 9.x | VCFA | Sr. Consultant | 19 |  | -19
Design and Deploy VCF Automation for VMware Cloud Foundation 5.x | AA | Virtualized Infrastructure 9.x | VCFA | PM | 12 |  | -12
Operate and Scale for Infrastructure |  | Operate and Scale for Infrastructure |  | Architect | 200 | 200 | 0
Operate and Scale for Infrastructure |  | Operate and Scale for Infrastructure |  | Sr. Consultant | 1200 | 1200 | 0
Operate and Scale for Infrastructure |  | Operate and Scale for Infrastructure |  | PM | 200 | 200 | 0
Transformation Consulting for Build a Private Cloud |  | Transformation Consulting for Build a Private Cloud |  | Architect | 80 | 80 | 0
Transformation Consulting for Build a Private Cloud |  | Transformation Consulting for Build a Private Cloud |  | Sr. Architect | 40 | 40 | 0
Transformation Consulting for Build a Private Cloud |  | Transformation Consulting for Build a Private Cloud |  | PM | 16 | 16 | 0
PSST |  |  |  | Sr. Consultant |  |  | 0 | 1664 | 1779
PSST |  |  |  | Architect |  |  | 0 | 373 | 394
PSST |  |  |  | Sr. Architect |  |  | 0 | 40 | 40
PSST |  |  |  | PM |  |  | 0 | 293 | 314
PSST |  |  |  | Sr. PM |  |  | 0 | 16 | 16
[5 empty] | 2399.8 | 2470.2 | 70.4 | 2386 | 2543 | 0
|  |  |  | Legend |  | VCF 5.2
VCF 9

## VCF 5.2 and 9 Tasks (hidden)
VCF 5.2 |  | VCF 5.2 |  |  | VCF 9.0 |  |  | Delta
|  | Architect | Sr. Con | PM | Architect | Sr. Con | PM | Architect | Sr. Con | PM
Project Management Oversight | Shared |  |  | 70 |  |  | 70 | 0 | 0 | 0
VMware Cloud Foundation Architecture Overview Workshop | Shared | 2 |  |  | 6 |  |  | 4 | 0 | 0
Customer Use Case Workshop | Shared | 5 |  |  | 8 |  |  | 3 | 0 | 0
VMware Cloud Foundation Design Decision and Design Consideration Workshop | Shared | 14 |  |  | 24 |  |  | 10 | 0 | 0
VMware Cloud Foundation Architecture Design Development | Shared | 9 |  |  | 16 |  |  | 7 | 0 | 0
VMware Cloud Foundation Prerequisites Workshop | Shared | 6 |  |  | 10 |  |  | 4 | 0 | 0
Identity and Access Management Design Workshop | Shared | 9 |  |  | 10 |  |  | 1 | 0 | 0
VMware Cloud Foundation+ Design Workshop | Shared | 2 | [5 empty] | -2 | 0 | 0
Update Design for VMware Cloud Foundation+ | Shared | 4 | [5 empty] | -4 | 0 | 0
VI workload domain architecture design development | Shared | 13 |  |  | 24 |  |  | 11 | 0 | 0
VI workload domain prerequisites workshop | Shared | 4 |  |  | 8 |  |  | 4 | 0 | 0
VMware Cloud Foundation NSX Workshop | Shared | 4 | 4 |  | 8 | 8 |  | 4 | 4 | 0
Networking Use Case Workshop | Shared | 6 |  |  | 8 |  |  | 2 | 0 | 0
NSX Edge Cluster Design Workshop for both Management and Workload Domains | Shared | 8 |  |  | 8 |  |  | 0 | 0 | 0
Aria Segment (Overlay or VLAN Backed) in the Management Domain Design Workshop | 5.2 Only | 4 | [5 empty] | -4 | 0 | 0
Update Design Documentation | Shared | 10 |  |  | 16 |  |  | 6 | 0 | 0
Environmental Validation and completion of the solution specification, and deployment parameters workbooks | Shared |  | 8 |  |  | 10 |  | 0 | 2 | 0
Prerequisite Checks, Imaging and Verification of ESXi Hosts | Shared |  | 30 |  |  | 40 |  | 0 | 10 | 0
Deployment of Cloud Foundation using Cloud Foundation Builder | 5.2 Only |  | 16 |  |  |  |  | 0 | -16 | 0
Deployment of Cloud Foundation using the VCF Installer Appliance | 9.0 Only |  |  |  |  | 24 |  | 0 | 24 | 0
Deployment of the VCF Identity Manager Appliance | Shared |  |  |  |  | 4 |  | 0 | 4 | 0
Functional testing of Cloud Foundation | Shared |  | 8 |  |  | 16 |  | 0 | 8 | 0
Deployment of the Regional Workspace ONE Access Instance | 5.2 Only |  | 4 |  |  |  |  | 0 | -4 | 0
Management Workload domain Identity and Access Management configuration | Shared |  | 8 |  |  | 8 |  | 0 | 0 | 0
VI Workload Domain Identity and Access Management configuration | Shared |  | 10 |  |  | 10 |  | 0 | 0 | 0
Identity and Access Management Configuration Functional Testing | Shared |  | 2 |  |  | 4 |  | 0 | 2 | 0
Validation of prerequisites for VMware Cloud Foundation+ | 5.2 Only |  | 2 |  |  |  |  | 0 | -2 | 0
Deployment of the vCenter Cloud Gateway Appliance for VMware Cloud Foundation+ | 5.2 Only |  | 2 |  |  |  |  | 0 | -2 | 0
VMware Cloud Foundation+ Subscription Activation | 5.2 Only |  | 2 |  |  |  |  | 0 | -2 | 0
Deploy VI workload domain per design specifications | Shared |  | 16 |  |  | 40 |  | 0 | 24 | 0
Validate VI workload domain deployment | Shared |  | 8 |  |  | 8 |  | 0 | 0 | 0
Deployment of Edge Cluster and Distributed Firewall Configurations for Management and Workload domains | Shared |  | 15 |  |  | 32 |  | 0 | 17 | 0
Deployment of Aria Suite Network Segment in the Management Domain | 5.2 Only |  | 4 |  |  |  |  | 0 | -4 | 0
Cloud Foundation Technical Knowledge Transfer Session | Shared |  | 2 |  |  | 4 |  | 0 | 2 | 0
Operational Enablement - Commissioning Hosts | Shared |  | 1 |  |  | 2 |  | 0 | 1 | 0
Operational Enablement - SDDC Manager Lifecycle Management (Basic Overview) | 5.2 Only |  | 1 |  |  |  |  | 0 | -1 | 0
Operational Enablement - VCF Operations Lifecycle Management (Basic Overview) | 9.0 Only |  |  |  |  | 2 |  | 0 | 2 | 0
Operational Enablement - VMware Cloud Foundation Support Process Workshop | 5.2 Only |  | 1 |  |  |  |  | 0 | -1 | 0
Identity and Access Control Knowledge Transfer | Shared |  | 1 |  |  | 2 |  | 0 | 1 | 0
VMware Cloud Foundation+ Knowledge Transfer | 5.2 Only |  | 1 |  |  |  |  | 0 | -1 | 0
Operational Enablement - Creating workload domains | Shared |  | 2 |  |  | 4 |  | 0 | 2 | 0
NSX with VMware Cloud Foundation Knowledge Transfer | Shared | 4 | 4 |  | 8 | 8 |  | 4 | 4 | 0
Totals |  | 104 | 152 | 70 | 154 | 226 | 70 | 50 | 74 | 0

## Issues (hidden)
Description | Owner | Status | Resolution
The LOE in the 5.2 WBS templates in the EDM do not agree with PSST | Daniel | Resolved
The VCF 5.2 WBS does not capture all the NSX scope included in the NSX PSST backlog item | Daniel | Resolved
The LOE in the 9.0 WBS templates in the EDM do not agree with PSST | Daniel | Resolved
The VCF 9 does not have yet WBS for third-party ecosystems optional backlog

## Title
VMware Solution
VMware and Customer Confidential
VMware Pro Cloud Service for Private Cloud
Component: VMware Cloud Foundation
Engagement Work Breakdown Structure
for
<Customer>
Prepared by
<Consultant>
Professional Services | VMware by Broadcom
<consultant>@broadcom.com

## VCF9 WBS - Medium Team
VMware Cloud Foundation 9.0.x - Work Breakdown Structure
Phase | Task | Architect | Senior Architect | Consultant | Senior Consultant | Project Manager | Senior Project Manager
|  | Total hours | Total Hours | Total Hours | Total hours | Total hours | Total Hours
Virtualized Infrastructure
VCF General
Design | Project Initiation (incl. Project Plan Validation and Workstream Alignment) |  |  |  |  | 52
| Project Kickoff |  |  |  |  | 4
| Path to Production |  |  |  |  | 8
| Requirements Gathering Workshop Development | 4
| Requirements Gathering Workshop | 2
| High Level Design Development | 6
| High Level Design Build | 4
| High Level Design Peer Review | 2
| High Level Design Customer Design Review & Sign-off Workshop | 1
| High Level Design Update | 2
VCF Infrastructure & Operations
Design | VCF Infrastructure & Operations Low Level Design Workshop Development for first VCF Fleet (Management & 1 Workload Domain) | 1
| VCF Infrastructure & Operations Low Level Design Workshop | 4
| VCF Infrastructure & Operations Low Level Design Build for Management Domain | 4
| VCF Infrastructure & Operations Low Level Design Build for 1 Workload Domain | 2
| VCF Infrastructure & Operations Low Level Design Peer Review | 1
| VCF Infrastructure & Operations Low Level Design Customer Design Review & Sign-off Workshop | 1
| VCF Infrastructure & Operations Low Level Design Update | 2
VCF Networking
Design | VCF Networking Low Level Design Workshop Development | 2
| VCF Networking Low Level Design Workshop | 5
| VCF Networking Low Level Design Development for one (1) Workload Domain | 5
| VCF Networking Low Level Design Peer Review | 2
| VCF Networking Low Level Design Customer Design Review & Sign-off Workshop | 1
| VCF Networking Low Level Design Update | 2
VCF Automation
Design | VCF Automation Low Level Design Development | 1
| VCF Automation Low Level Design Workshop | 2
| VCF Automation Low Level Design for one (1) multi-tenancy Design Workshop | 2
| VCF Automation Low Level Design Build | 3
| VCF Automation Low Level Design Peer Review | 1
| VCF Automation Low Level Design Customer Design Review & Sign-off Workshop | 1
| VCF Automation Low Level Design Update | 1
VCF Deployment
Deploy | VCF Infrastructure, Operations & Networking Prerequisites Workshop |  |  |  | 40
| VCF Infrastructure & Operations Bring-up prerequisites check and validation using the Planning and Preparation Workbook |  |  |  | 20
| VCF Infrastructure & Operations Deployment of the VCF Fleet using the VCF Installer Appliance (including VCFA & VCFO) |  |  |  | 8
| VCF Infrastructure & Operations Deployment of NSX Edge Cluster for the Management Workload Domain |  |  |  | 4
| VCF Infrastructure & Operations Functional Testing and Validation of VCF - Management Domain |  |  |  | 14
| VCF Infrastructure & Operations Workload Domain deployment prerequisites check and validation using the Planning and Preparation Workbook |  |  |  | 10
| VCF Infrastructure & Operations Deployment of one (1) Workload Domain |  |  |  | 40
| VCF Infrastructure & Operations Deployment of NSX Edge Cluster for one (1) Workload Domain |  |  |  | 4
| VCF Infrastructure & Operations Functional Testing and Validation of VCF - Workload Domain |  |  |  | 14
| VCF Infrastructure, Operations & Networking Test & Acceptance Development |  |  |  | 2
| VCF Infrastructure, Operations & Networking Test & Acceptance |  |  |  | 2
| VCF Infrastructure, Operations & Networking Knowledge Transfer Workshop Development |  |  |  | 5
| VCF Infrastructure, Operations & Networking Knowledge Transfer Workshop |  |  |  | 13
VCF Automation
Deploy | VCF Automation Prerequisites Workshop |  |  |  | 4
| VCF Automation Finalize the Planning and Preparation and/or Configuration Workbook with the Automation Configuration |  |  |  | 2
| VCF Automation Verify the Load Balancer VIP CNAMES for the Appliance FQDNs are configured and registered properly in DNS |  |  |  | 1
| VCF Automation Import the certificates for the VCF Automation appliances |  |  |  | 1
| VCF Automation Discuss and Implement VCF Automation Tenancy configuration |  |  |  | 6
| VCF Automation Verify customer VM network, Active Directory, vCenter infrastructure and virtual machine templates are ready and available |  |  |  | 1
| VCF Automation Create VCF Automation provider and organizational configuration |  |  |  | 6
| VCF Automation Cloud Assembly - Configure Cloud Accounts |  |  |  | 1
| VCF Automation Cloud Assembly - Configure Projects, Cloud Zones, Flavor Mappings, Image Mappings, Network Profiles, and Storage Profiles |  |  |  | 2
| VCF Automation Create VCF Automation Cloud Template for example configuration |  |  |  | 4
| VCF Automation Functional Testing and Validation |  |  |  | 2
| VCF Automation Test & Acceptance Assistance |  |  |  | 2
| VCF Automation Test & Acceptance Customer Review & Sign-off Workshop |  |  |  | 1
| VCF Automation Knowledge Transfer Workshop Development |  |  |  | 1
| VCF Automation Knowledge Transfer Workshop |  |  |  | 4
| VCF Automation - Operational Enablement - VCF Automation Service Catalog Management Workshop |  |  |  | 3
| VCF Automation - Operational Enablement - VCF Automation Troubleshooting, Event and Log Management Workshop |  |  |  | 2
| VCF Automation - Operational Enablement - VCF Automation Enable customer on Startup/Shutdown procedures |  |  |  | 4
| VCF Automation - Operational Enablement - VCF Automation Single Machine Blueprint Creation Workshop |  |  |  | 6
| VCF Automation - Operational Enablement - VCF Automation Custom Forms, Actions, and Subscriptions Workshop |  |  |  | 4
VCF Post Deployment
Deploy | Deploy Foundational Integration - DNS |  |  |  | 20
| Deploy Foundational Integration - IPAM |  |  |  | 40
| Deploy Foundational Integration - AD |  |  |  | 20
| VCF Backup Configuration |  |  |  | 1
| Certificate Replacement of VCF Management Components |  |  |  | 4
| Certificate Replacement of one (1) workload domain |  |  |  | 2 |  |  | Total:
Total for Virtual Infrastructure |  | 64 | 0 | 0 | 320 | 64 | 0 | 448
Automated Operations
VCF Operations for Logs
Design | Project Management Oversight |  |  |  |  | 16
| VCF Operations for Logs Low Level Design Development | 2
| VCF Operations for Logs Low Level Design Workshop | 2
| VCF Operations for Logs Low Level Design Build | 1 |  |  | 2
| VCF Operations for Logs Low Level Design Peer Review | 1
| VCF Operations for Logs Low Level Design Customer Design Review & Sign-off Workshop | 1
| VCF Operations for Logs Low Level Design Update | 1
Deploy VCF Operations for Logs
Deploy | VCF Operations for Logs Prerequisites Workshop |  |  |  | 2
| VCF Operations for Logs Configuration |  |  |  | 4
| VCF Operations for Logs Functional Testing and Validation |  |  |  | 2
| VCF Operations for Logs Test & Acceptance Development |  |  |  | 1
| VCF Operations for Logs Test & Acceptance |  |  |  | 2
| VCF Operations for Logs Knowledge Transfer Workshop Development |  |  |  | 1
| VCF Operations for Logs Knowledge Transfer Workshops: |  |  |  | -
| VCF Operations for Logs - Product Knowledge Transfer: Review and discussion of common use cases with customer |  |  |  | 3
| VCF Operations for Logs - Product Knowledge Transfer: Review of out-of-the-box dashboards with customer |  |  |  | 2
| VCF Operations for Logs - Product Knowledge Transfer: Review of Interactive Analytics view, create filters with customer |  |  |  | 2
| VCF Operations for Logs - Product Knowledge Transfer: Review of Content Pack Marketplace with customer |  |  |  | 2
| VCF Operations for Logs - Product Knowledge Transfer: Creation of sample dashboard with customer |  |  |  | 6
| VCF Operations for Logs - Adoption Knowledge Transfer: Review of health monitoring, scaling, and start-up/shutdown procedures with customer |  |  |  | 2
VCF Operations for Networks
Design | VCF Operations for Networks Low Level Design Development | 2
| VCF Operations for Networks Low Level Design Workshop | 2
| VCF Operations for Networks Low Level Design Build | 1 |  |  | 4
| VCF Operations for Networks Low Level Design Peer Review | 1
| VCF Operations for Networks Low Level Design Customer Design Review & Sign-off Workshop | 1
| VCF Operations for Networks Low Level Design Update | 1
Deploy VCF Operations for Networks
Deploy | VCF Operations for Networks Prerequisites Workshop |  |  |  | 2
| VCF Operations for Networks Configuration |  |  |  | 6
| VCF Operations for Networks Functional Testing and Validation |  |  |  | 2
| VCF Operations for Networks Test & Acceptance Development |  |  |  | 1
| VCF Operations for Networks Test & Acceptance |  |  |  | 2
| VCF Operations for Networks Knowledge Transfer Workshop Development |  |  |  | 16
| VCF Operations for Networks Knowledge Transfer Workshop |  |  |  | 16 |  |  | Total:
Total for Automated Operations |  | 16 | 0 | 0 | 80 | 16 | 0 | 112
Security Governance and Compliance
Design Access & Identity
Design | Project Management Oversight |  |  |  |  | 34
| VCF Access & Identity Low Level Design Workshop Development | 2
| VCF Access & Identity Low Level Design Workshop | 4
| VCF Access & Identity Low Level Design Build | 3
| VCF Access & Identity Low Level Design Peer Review | 1
| VCF Access & Identity Customer Review & Sign-off Workshop | 1
| VCF Access & Identity Low Level Design Update | 1
Design NIST Hardening
Design | VCF NIST Hardening Low Level Design Workshop Development | 4
| VCF NIST Hardening Low Level Design Workshop | 9
| VCF NIST Hardening Low Level Design Build | 6
| VCF NIST Hardening Low Level Design Customer Review & Sign-off Workshop | 1
| VCF NIST Hardening Low Level Design Update | 2
Deploy Access & Identity
Deploy | VCF Access & Identity Build |  |  |  | 4
| VCF Access & Identity Configuration |  |  |  | 4
| VCF Access & Identity Functional Testing and Validation |  |  |  | 4
| VCF Access & Identity Knowledge Transfer Workshop Development |  |  |  | 1
| VCF Access & Identity Knowledge Transfer Workshop |  |  |  | 3
VCF NIST Hardening
Deploy | VCF NIST Hardening Configuration |  |  |  | 146
| VCF NIST Hardening Functional Testing and Validation |  |  |  | 4
| VCF NIST Hardening Knowledge Transfer Workshop Development |  |  |  | 1
| VCF NIST Hardening Knowledge Transfer Workshop |  |  |  | 3 |  |  | Total:
Total for Security Governance and Compliance |  | 34 | 0 | 0 | 170 | 34 | 0 | 238
Transformation Consulting
Design | Project Management Oversight | [5 empty] | 16
| Transformation Consulting Work for Build a Private Cloud | 80 | 40 |  |  |  |  | Total:
Total for Transformation Consulting |  | 80 | 40 | 0 | 0 | 0 | 16 | 136
[7 empty] | Grand Total: | 934

## LOE summary (hidden)
Role | SUM of 5.2 WBS LOE | SUM of 9.0 WBS LOE | SUM of 5.2 PSST LOE | SUM of 9.0 PSST LOE | #VALUE!
Architect | 575 | 607 | 373 | 394 | 21
PM | 361.8 | 346.2 | 293 | 314 | 21
Sr. Architect | 40 | 40 | 40 | 40 | 0
Sr. Consultant | 1423 | 1477 | 1664 | 1779 | 115
Sr. PM |  |  | 16 | 16 | 0
Grand Total | 2399.8 | 2470.2 | 2386 | 2543