## Analysis (hidden)
5.2 Backlog | 5.2 WBS Name | 9.0 Backlog | 9.0 WBS Name | Role | 5.2 WBS LOE | 9.0 WBS LOE | Delta | 5.2 PSST LOE | 9.0 PSST LOE
Design and Deploy VMware Cloud Foundation 5.x (see task details tab) | VCF | Virtualized Infrastructure 9.x | VCF | Architect | 104 | 154 | 50
Design and Deploy VMware Cloud Foundation 5.x (see task details tab) | VCF | Virtualized Infrastructure 9.x | VCF | Sr. Consultant | 152 | 226 | 74
Design and Deploy VMware Cloud Foundation 5.x | VCF | Virtualized Infrastructure 9.x | VCF | PM | 70 | 70 | 0
Design and Deploy NSX with VMware Cloud Foundation 5.x |  | Virtualized Infrastructure 9.x |  | Architect |  |  | 0
Design and Deploy NSX with VMware Cloud Foundation 5.x |  | Virtualized Infrastructure 9.x |  | Sr. Consultant |  |  | 0
Design and Deploy NSX with VMware Cloud Foundation 5.x |  | Virtualized Infrastructure 9.x |  | PM |  |  | 0
Deploy Security Hardening for VMware Cloud Foundation | VCF_Security | Security Governance, and Compliance 9.x | VCF_Security | Architect | 140 | 140 | 0
Deploy Security Hardening for VMware Cloud Foundation | VCF_Security | Security Governance, and Compliance 9.x | VCF_Security | PM | 35 | 35 | 0
Design and Implement Aria Suite Lifecycle and Access Management With VMware Cloud Foundation 5.x | ASLC | Virtualized Infrastructure 9.x |  | Architect | 4 |  | -4
Design and Implement Aria Suite Lifecycle and Access Management With VMware Cloud Foundation 5.x | ASLC | Virtualized Infrastructure 9.x |  | Sr. Consultant | 8 |  | -8
Design and Implement Aria Suite Lifecycle and Access Management With VMware Cloud Foundation 5.x | ASLC | Virtualized Infrastructure 9.x |  | PM | 3.6 |  | -3.6
Design and Deploy VMware Cloud Foundation® Operations for networks for VMware Cloud Foundation® 5.x | AOPS | Automated Operations 9.x | VCFO | Architect | 16 | 16 | 0
Design and Deploy VMware Cloud Foundation® Operations for networks for VMware Cloud Foundation® 5.x | AOPS | Automated Operations 9.x | VCFO | Sr. Consultant | 16 | 24 | 8
Design and Deploy VMware Cloud Foundation® Operations for networks for VMware Cloud Foundation® 5.x | AOPS | Automated Operations 9.x | VCFO | PM | 12 | 12 | 0
Design and Deploy VCF Operations for Logs for VMware Cloud Foundation 5.x | AOPS4L | Automated Operations 9.x | VCFOL | Architect | 10 | 8 | -2
Design and Deploy VCF Operations for Logs for VMware Cloud Foundation 5.x | AOPS4L | Automated Operations 9.x | VCFOL | Sr. Consultant | 12 | 12 | 0
Design and Deploy VCF Operations for Logs for VMware Cloud Foundation 5.x | AOPS4L | Automated Operations 9.x | VCFOL | PM | 6 | 6 | 0
Design and Deploy VMware Cloud Foundation® Operations for networks for VMware Cloud Foundation® 5.x | AOPS4N | Virtualized Infrastructure 9.x | VCFON | Architect | 5 | 9 | 4
Design and Deploy VMware Cloud Foundation® Operations for networks for VMware Cloud Foundation® 5.x | AOPS4N | Virtualized Infrastructure 9.x | VCFON | Sr. Consultant | 16 | 15 | -1
Design and Deploy VMware Cloud Foundation® Operations for networks for VMware Cloud Foundation® 5.x | AOPS4N | Virtualized Infrastructure 9.x | VCFON | PM | 7.2 | 7.2 | 0
Design and Deploy VCF Automation for VMware Cloud Foundation 5.x | AA | Virtualized Infrastructure 9.x | VCFA | Architect | 16 |  | -16
Design and Deploy VCF Automation for VMware Cloud Foundation 5.x | AA | Virtualized Infrastructure 9.x | VCFA | Sr. Consultant | 19 |  | -19
Design and Deploy VCF Automation for VMware Cloud Foundation 5.x | AA | Virtualized Infrastructure 9.x | VCFA | PM | 12 |  | -12
Operate and Scale for Infrastructure |  | Operate and Scale for Infrastructure |  | Architect | 200 | 200 | 0
Operate and Scale for Infrastructure |  | Operate and Scale for Infrastructure |  | Sr. Consultant | 1200 | 1200 | 0
Operate and Scale for Infrastructure |  | Operate and Scale for Infrastructure |  | PM | 200 | 200 | 0
Transformation Consulting for Build a Private Cloud |  | Transformation Consulting for Build a Private Cloud |  | Architect | 80 | 80 | 0
Transformation Consulting for Build a Private Cloud |  | Transformation Consulting for Build a Private Cloud |  | Sr. Architect | 40 | 40 | 0
Transformation Consulting for Build a Private Cloud |  | Transformation Consulting for Build a Private Cloud |  | PM | 16 | 16 | 0
PSST |  |  |  | Sr. Consultant |  |  | 0 | 1664 | 1779
PSST |  |  |  | Architect |  |  | 0 | 373 | 394
PSST |  |  |  | Sr. Architect |  |  | 0 | 40 | 40
PSST |  |  |  | PM |  |  | 0 | 293 | 314
PSST |  |  |  | Sr. PM |  |  | 0 | 16 | 16
[5 empty] | 2399.8 | 2470.2 | 70.4 | 2386 | 2543 | 0
|  |  |  | Legend |  | VCF 5.2
VCF 9

## VCF 5.2 and 9 Tasks (hidden)
VCF 5.2 |  | VCF 5.2 |  |  | VCF 9.0 |  |  | Delta
|  | Architect | Sr. Con | PM | Architect | Sr. Con | PM | Architect | Sr. Con | PM
Project Management Oversight | Shared |  |  | 70 |  |  | 70 | 0 | 0 | 0
VMware Cloud Foundation Architecture Overview Workshop | Shared | 2 |  |  | 6 |  |  | 4 | 0 | 0
Customer Use Case Workshop | Shared | 5 |  |  | 8 |  |  | 3 | 0 | 0
VMware Cloud Foundation Design Decision and Design Consideration Workshop | Shared | 14 |  |  | 24 |  |  | 10 | 0 | 0
VMware Cloud Foundation Architecture Design Development | Shared | 9 |  |  | 16 |  |  | 7 | 0 | 0
VMware Cloud Foundation Prerequisites Workshop | Shared | 6 |  |  | 10 |  |  | 4 | 0 | 0
Identity and Access Management Design Workshop | Shared | 9 |  |  | 10 |  |  | 1 | 0 | 0
VMware Cloud Foundation+ Design Workshop | Shared | 2 | [5 empty] | -2 | 0 | 0
Update Design for VMware Cloud Foundation+ | Shared | 4 | [5 empty] | -4 | 0 | 0
VI workload domain architecture design development | Shared | 13 |  |  | 24 |  |  | 11 | 0 | 0
VI workload domain prerequisites workshop | Shared | 4 |  |  | 8 |  |  | 4 | 0 | 0
VMware Cloud Foundation NSX Workshop | Shared | 4 | 4 |  | 8 | 8 |  | 4 | 4 | 0
Networking Use Case Workshop | Shared | 6 |  |  | 8 |  |  | 2 | 0 | 0
NSX Edge Cluster Design Workshop for both Management and Workload Domains | Shared | 8 |  |  | 8 |  |  | 0 | 0 | 0
Aria Segment (Overlay or VLAN Backed) in the Management Domain Design Workshop | 5.2 Only | 4 | [5 empty] | -4 | 0 | 0
Update Design Documentation | Shared | 10 |  |  | 16 |  |  | 6 | 0 | 0
Environmental Validation and completion of the solution specification, and deployment parameters workbooks | Shared |  | 8 |  |  | 10 |  | 0 | 2 | 0
Prerequisite Checks, Imaging and Verification of ESXi Hosts | Shared |  | 30 |  |  | 40 |  | 0 | 10 | 0
Deployment of Cloud Foundation using Cloud Foundation Builder | 5.2 Only |  | 16 |  |  |  |  | 0 | -16 | 0
Deployment of Cloud Foundation using the VCF Installer Appliance | 9.0 Only |  |  |  |  | 24 |  | 0 | 24 | 0
Deployment of the VCF Identity Manager Appliance | Shared |  |  |  |  | 4 |  | 0 | 4 | 0
Functional testing of Cloud Foundation | Shared |  | 8 |  |  | 16 |  | 0 | 8 | 0
Deployment of the Regional Workspace ONE Access Instance | 5.2 Only |  | 4 |  |  |  |  | 0 | -4 | 0
Management Workload domain Identity and Access Management configuration | Shared |  | 8 |  |  | 8 |  | 0 | 0 | 0
VI Workload Domain Identity and Access Management configuration | Shared |  | 10 |  |  | 10 |  | 0 | 0 | 0
Identity and Access Management Configuration Functional Testing | Shared |  | 2 |  |  | 4 |  | 0 | 2 | 0
Validation of prerequisites for VMware Cloud Foundation+ | 5.2 Only |  | 2 |  |  |  |  | 0 | -2 | 0
Deployment of the vCenter Cloud Gateway Appliance for VMware Cloud Foundation+ | 5.2 Only |  | 2 |  |  |  |  | 0 | -2 | 0
VMware Cloud Foundation+ Subscription Activation | 5.2 Only |  | 2 |  |  |  |  | 0 | -2 | 0
Deploy VI workload domain per design specifications | Shared |  | 16 |  |  | 40 |  | 0 | 24 | 0
Validate VI workload domain deployment | Shared |  | 8 |  |  | 8 |  | 0 | 0 | 0
Deployment of Edge Cluster and Distributed Firewall Configurations for Management and Workload domains | Shared |  | 15 |  |  | 32 |  | 0 | 17 | 0
Deployment of Aria Suite Network Segment in the Management Domain | 5.2 Only |  | 4 |  |  |  |  | 0 | -4 | 0
Cloud Foundation Technical Knowledge Transfer Session | Shared |  | 2 |  |  | 4 |  | 0 | 2 | 0
Operational Enablement - Commissioning Hosts | Shared |  | 1 |  |  | 2 |  | 0 | 1 | 0
Operational Enablement - SDDC Manager Lifecycle Management (Basic Overview) | 5.2 Only |  | 1 |  |  |  |  | 0 | -1 | 0
Operational Enablement - VCF Operations Lifecycle Management (Basic Overview) | 9.0 Only |  |  |  |  | 2 |  | 0 | 2 | 0
Operational Enablement - VMware Cloud Foundation Support Process Workshop | 5.2 Only |  | 1 |  |  |  |  | 0 | -1 | 0
Identity and Access Control Knowledge Transfer | Shared |  | 1 |  |  | 2 |  | 0 | 1 | 0
VMware Cloud Foundation+ Knowledge Transfer | 5.2 Only |  | 1 |  |  |  |  | 0 | -1 | 0
Operational Enablement - Creating workload domains | Shared |  | 2 |  |  | 4 |  | 0 | 2 | 0
NSX with VMware Cloud Foundation Knowledge Transfer | Shared | 4 | 4 |  | 8 | 8 |  | 4 | 4 | 0
Totals |  | 104 | 152 | 70 | 154 | 226 | 70 | 50 | 74 | 0

## Issues (hidden)
Description | Owner | Status | Resolution
The LOE in the 5.2 WBS templates in the EDM do not agree with PSST | Daniel | Resolved
The VCF 5.2 WBS does not capture all the NSX scope included in the NSX PSST backlog item | Daniel | Resolved
The LOE in the 9.0 WBS templates in the EDM do not agree with PSST | Daniel | Resolved
The VCF 9 does not have yet WBS for third-party ecosystems optional backlog

## VCF9 SGC - Medium Team
VMware Cloud Foundation 9.0.x - Work Breakdown Structure
Phase | Task | Architect | Senior Consultant | Project Manager
|  | Total hours | Total hours | Total hours
Security Governance and Compliance
VCF Security Hardening
Design | Project Management Oversight |  |  | 22
| VCF Hardening Workshop Development | 12 | 8
| VCF Hardening Workshop | 8 | 8
| VCF Hardening Customer Review & Sign-off Workshop | 2 | 2
| Prep Tools and Scripts |  | 16
| VCF Knowledge Transfer Workshop Development |  | 1
| VCF Knowledge Transfer Workshop |  | 3
VCF NIST Hardening
Deploy | Project Management Oversight |  |  | 12
| Configure Hardening |  | 124
| Validate Hardening | 12 | 8 |  | Total:
Total for Security Governance and Compliance |  | 34 | 170 | 34 | 238
|  |  |  | Grand Total: | 238

## LOE summary (hidden)
Role | SUM of 5.2 WBS LOE | SUM of 9.0 WBS LOE | SUM of 5.2 PSST LOE | SUM of 9.0 PSST LOE | #VALUE!
Architect | 575 | 607 | 373 | 394 | 21
PM | 361.8 | 346.2 | 293 | 314 | 21
Sr. Architect | 40 | 40 | 40 | 40 | 0
Sr. Consultant | 1423 | 1477 | 1664 | 1779 | 115
Sr. PM |  |  | 16 | 16 | 0
Grand Total | 2399.8 | 2470.2 | 2386 | 2543