## Title
VMware Solution
VMware and Customer Confidential
VMware Pro Cloud Service for Private Cloud Infrastructure
Component: VMware Cloud Foundation Operations
Engagement Work Breakdown Structure
for
<Customer>
Prepared by
<Consultant>
Professional Services | VMware by Broadcom
<consultant>@broadcom.com

## VCFO WBS
VMware Cloud Foundation 9.0 - Operations - Work Breakdown Structure
Backlog Item | Task | Architect | Senior Consultant | Project Manager
|  | Total hours | Total hours | Total hours
Project Management Oversight - 30% | Project Management Oversight |  |  | 12
VMware Cloud Foundation Operations Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Discuss Environmental requirements for Aria Operations design workshop | 2
VMware Cloud Foundation Operations Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Import VCF Operations Certificates to Fleet Management | 1
VMware Cloud Foundation Operations Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Discover current environment workshop - 3rd Party integration points | 1
VMware Cloud Foundation Operations Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Discover current environment workshop - virtual resource allocation/accounting practices and policies | 1
VMware Cloud Foundation Operations Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Discover current environment workshop - Application Discovery and Monitoring Requirements | 1
VMware Cloud Foundation Operations Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Discover future environment workshop - infrastructure trends, planned growth | 1
VMware Cloud Foundation Operations Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Discover future environment workshop - advanced configuration requirements/use cases (dashboards, policies, supermetrics, alerts, user access, etc.) | 2
VMware Cloud Foundation Operations Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Design and document - integration points requirements (management packs, etc.) | 1
VMware Cloud Foundation Operations Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Finalize Solution Design and Diagrams document | 2
VMware Cloud Foundation Operations Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Design review workshop | 4
VMware Cloud Foundation Operations Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Deployment of VCF Operations from Fleet Management |  | 4
VMware Cloud Foundation Operations Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Cluster validation with all nodes deployed, validate cluster health |  | 2
VMware Cloud Foundation Operations Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Finalize Solution Specification Workbook |  | 1
VMware Cloud Foundation Operations Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Product/Use Case Knowledge Transfer: General product training including foundation use case discussions, only basic customization |  | 2
VMware Cloud Foundation Operations Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Product Knowledge Transfer: Discuss proper cluster start-up and shutdown procedures |  | 0.5
VMware Cloud Foundation Operations Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Product Knowledge Transfer: Discuss self-monitoring capabilities of Aria Operations (from within GUI only) |  | 0.5
VMware Cloud Foundation Operations Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Product Knowledge Transfer: Discuss how to add capacity to a cluster, if needed |  | 0.5
VMware Cloud Foundation Operations Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Product Knowledge Transfer: Create sample simple dashboard |  | 1
VMware Cloud Foundation Operations Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Product Knowledge Transfer: Create sample simple supermetric |  | 1
VMware Cloud Foundation Operations Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Product Knowledge Transfer: Create sample simple report |  | 1
VMware Cloud Foundation Operations Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Product Knowledge Transfer: Discuss and supervise customer-led enablement of predictive DRS within vCenter |  | 1
VMware Cloud Foundation Operations Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Adoption Knowledge Transfer: User/groups persona workshop, specific to customer environment, but limited custom groups |  | 2
VMware Cloud Foundation Operations Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Adoption Knowledge Transfer: Review out-of-the-box dashboards, configure dashboards to reduce "dashboard" overload, specific to customer environment |  | 3.5
VMware Cloud Foundation Operations Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Adoption Knowledge Transfer: Review active alerts, configure alerts to reduce "alert" noise, specific to customer environment |  | 2
VMware Cloud Foundation Operations Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Adoption Knowledge Transfer: Discuss proactive monitoring capabilities, specific to customer's environment |  | 2