## Title
VMware Solution
VMware and Customer Confidential
VMware Pro Cloud Service for Private Cloud Infrastructure
Component: VMware Cloud Foundation Operations for Networks
Engagement Work Breakdown Structure
for
<Customer>
Prepared by
<Consultant>
Professional Services | VMware by Broadcom
<consultant>@broadcom.com

## VCFON WBS
VMware Cloud Foundation 9.0 - Operations for Networks - Work Breakdown Structure
Backlog Item | Task | Architect | Senior Consultant | Project Manager
|  | Total hours | Total hours | Total hours
Project Management Oversight - 30% | Project Management Oversight |  |  | 7.2
VMware Cloud Foundation Operations for Networks Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Design workshop - VMware Cloud Foundation Operations for Networks | 3
VMware Cloud Foundation Operations for Networks Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Design and document - VMware Cloud Foundation Operations for Networks Architecture | 2
VMware Cloud Foundation Operations for Networks Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Architecture Finalize Solution Checklist | 1
VMware Cloud Foundation Operations for Networks Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Finalize architecture design diagrams | 2
VMware Cloud Foundation Operations for Networks Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Design review workshop | 1
VMware Cloud Foundation Operations for Networks Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Deploy and configure Platform virtual machine(s) |  | 3
VMware Cloud Foundation Operations for Networks Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Deploy proxy virtual machine(s) |  | 2
VMware Cloud Foundation Operations for Networks Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Configure datasources |  | 2
VMware Cloud Foundation Operations for Networks Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Validate of VMware Cloud Foundation Operations for Networks installation |  | 2
VMware Cloud Foundation Operations for Networks Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Finalize Installation and configuration procedures document |  | 1
VMware Cloud Foundation Operations for Networks Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Finalize Configuration workbook |  | 1
VMware Cloud Foundation Operations for Networks Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | General Product Training |  | 1
VMware Cloud Foundation Operations for Networks Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Knowledge Transfer for Foundational Use Cases |  | 3