## Title
VMware Solution
VMware and Customer Confidential
VMware Pro Cloud Service for Private Cloud Infrastructure
Component: VMware Cloud Foundation Operations for logs
Engagement Work Breakdown Structure
for
<Customer>
Prepared by
<Consultant>
Professional Services | VMware by Broadcom
<consultant>@broadcom.com

## VCFOL WBS
VMware Cloud Foundation 9.0 - Operations for Logs - Work Breakdown Structure
Backlog Item | Task | Architect | Senior Consultant | Project Manager
|  | Total hours | Total hours | Total hours
Project Management Oversight - 30% | Project Management Oversight |  |  | 6
VMwre Cloud Foundation Operations for Logs Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Discuss Environmental requirements for VMwre Cloud Foundation Operations for Logs design workshop | 2
VMwre Cloud Foundation Operations for Logs Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Discover current environment workshop - 3rd Party integration points | 0.5
VMwre Cloud Foundation Operations for Logs Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Discover current environment workshop - virtual resource allocation/accounting practices and policies | 0.5
VMwre Cloud Foundation Operations for Logs Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Discover future environment workshop - infrastructure trends, planned growth | 0.5
VMwre Cloud Foundation Operations for Logs Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Discover future environment workshop - advanced configuration requirements/use cases (dashboards, policies, alerts, user access, custom content pack scoping, etc.)) | 1
VMwre Cloud Foundation Operations for Logs Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Design and document - number of VMwre Cloud Foundation Operations for Logs instances | 0.5
VMwre Cloud Foundation Operations for Logs Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Design and document - sizing for each VMwre Cloud Foundation Operations for Logs instance | 0.5
VMwre Cloud Foundation Operations for Logs Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Design and document - forwarder requirements | 0.5
VMwre Cloud Foundation Operations for Logs Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Finalize solution design and diagrams documents | 1
VMwre Cloud Foundation Operations for Logs Design for VMware Pro Cloud Service for Private Cloud Infrastructure | Design review workshop | 1
VMwre Cloud Foundation Operations for Logs Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Deployment of VMwre Cloud Foundation Operations for Logs from VMwre Cloud Foundation Suite Lifecycle |  | 4
VMwre Cloud Foundation Operations for Logs Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Cluster Validation with all nodes deployed, validate cluster health |  | 1
VMwre Cloud Foundation Operations for Logs Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Finalization of Solution Specification and Validation Workbooks |  | 1
VMwre Cloud Foundation Operations for Logs Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Product Knowledge Transfer: Review and discussion of common use cases with customer |  | 1
VMwre Cloud Foundation Operations for Logs Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Product Knowledge Transfer: Review of out-of-the-box dashboards with customer |  | 1
VMwre Cloud Foundation Operations for Logs Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Product Knowledge Transfer: Review of Interactive Analytics view, create filters with customer |  | 1
VMwre Cloud Foundation Operations for Logs Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Product Knowledge Transfer: Review of Content Pack Marketplace with customer |  | 1
VMwre Cloud Foundation Operations for Logs Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Product Knowledge Transfer: Creation of sample dashboard with customer |  | 1
VMwre Cloud Foundation Operations for Logs Deployment for VMware Pro Cloud Service for Private Cloud Infrastructure | Adoption Knowledge Transfer: Review of health monitoring, scaling, and start-up/shutdown procedures with customer |  | 1