## Title
VMware Solution
VMware and Customer Confidential
VMware Pro Cloud Service for Private Cloud Infrastructure
Component: VMware Cloud Foundation vSphere Kubernetes Service Add-on
Engagement Work Breakdown Structure
for
<Customer>
Prepared by
<Consultant>
Professional Services | VMware by Broadcom
<consultant>@broadcom.com

## VCF VKS WBS
VMware Cloud Foundation 9.0.x - vSphere Kubernetes Service Add-on - Work Breakdown Structure
Backlog Item | Task | Architect | Senior Consultant | Project Manager
|  | Total hours | Total hours | Total hours
Project Management Oversight - 30% | Project Management Oversight |  |  | 12
VMware Cloud Foundation vSphere Kubernetes Service Consume Service | VMware Cloud Foundation vSphere Kubernetes Service Workshop | 4 | 4
VMware Cloud Foundation vSphere Kubernetes Service Consume Service | vSphere Kubernetes Service Use Case Workshop | 2 | 2
VMware Cloud Foundation vSphere Kubernetes Service Consume Service | vSphere Kuberenetes Service Supervisor Cluster Workshop | 2 | 2
VMware Cloud Foundation vSphere Kubernetes Service Consume Service | Create Design Documents | 8
VMware Cloud Foundation vSphere Kubernetes Service Consume Service | Cloud Foundation vSphere Kubernetes Service Prerequisites Workshop |  | 4
VMware Cloud Foundation vSphere Kubernetes Service Consume Service | Create Solution Specification and Verification workbooks |  | 4
VMware Cloud Foundation vSphere Kubernetes Service Consume Service | Configuration of vSphere Kubernetes Service Supervisor Cluster |  | 4
VMware Cloud Foundation vSphere Kubernetes Service Consume Service | Perform verification of the deployment |  | 2
VMware Cloud Foundation vSphere Kubernetes Service Consume Service | Cloud Foundation - vSphere Kubernetes Service Knowledge Transfer |  | 2